Department of Mechanical and Industrial Engineering

Mechanical Engineering

| Course Number | MEC713 |
| --- | --- |
| Course Title | Project Management |
| Semester/Year | Fall/2023 |
| Professor name | Dr. Sajad Saeedi |
| T.A name | Feze Golshani Gharie Ali |
| Section | 03 |
| Group | 04 |

| Assignment No. |  | 4 |
| --- | --- | --- |

| Submission Date | 20 November, 2023 |
| --- | --- |
| Due Date | 22 November, 2023 |

| Student Name | Student ID | Signature* |
| --- | --- | --- |
| Farris Hamid | 501034692 |  |

(Note: Remove the first 4 digits from your student ID)

*By signing above you attest that you have contributed to this submission and confirm that all work you have contributed to this submission is your own work.  Any suspicion of copying or plagiarism in this work will result in an investigation of Academic Misconduct and may result in a “0” on the work, an “F” in the course, or possibly more severe penalties, as well as a Disciplinary Notice on your academic record under the Student Code of Academic Conduct, which can be found online at: http://www.ryerson.ca/senate/policies/pol60.pdf.

Solve the following problems and upload the file of solutions in the D2L. You may type the  solutions in Microsoft Word and upload the file, or you may scan your solutions by scanner and  upload the file in the D2L (due date: Wednesday, November 22, 11:59 am, no extension!).

1. (20 points)

a. What is an activity slope and what does it indicate?

An activity slope, also known as a resource allocation slope, is a project management concept that illustrates the rate at which resources are allocated to a specific project activity over time. As the activity continues, it depicts the gradual or abrupt rise and decrease of resources (such as labour, equipment, or funds). The activity slope reveals how resources are allocated and utilized within a project, which can have significant consequences for project scheduling, cost management, and overall project success.

The activity slope formula is expressed as:

Activity Slope=Crash Cost - Normal CostCrash Time - Normal Time

b. What are two methods for addressing the constrained resources allocation problem?

The two methods for dealing with resource constraints in project management are:

- Heuristic Approach: This approach in project management involves using rules of thumb, practical guidelines, or experience-based techniques to make decisions and solve problems. This approach is often used when dealing with complex and uncertain situations, as they provide quick and practical solutions that may not be guaranteed to be the absolute best. This approach is also used to help project managers make decisions efficiently, even when complete information or a perfect solution is not available.

- Optimization Approach: This approach in project management involves the use of models, algorithms, and analytical methods to find the best possible solution to a problem. This approach also aims to maximize or minimize a specific objective, such as project completion time, cost, or resource allocation, by systematically evaluating all possible options and selecting the one that optimizes the chosen objective. Optimization techniques can be highly effective for finding the most efficient and cost-effective solutions to complex project management problems.

2. (20 points)

a. What is the purpose of “earned value”? How would the progress of the project as a whole be calculated?

The purpose of “earned value” (EV) in project management is to measure and track the performance of a project in terms of cost and schedule. It helps project managers assess whether a project is on track, ahead of schedule, or behind schedule and whether it is under or over budget. Earned value provides a standardized and objective way to evaluate project progress.

The progress of the project would be calculated by calculating the EV by multiplying the percentage complete by the total project budget. It is expressed as:

EV=% complete × Budget at Completion

b. What are the primary difficulties experienced in the design of project reports? Mention four of  them.

The primary difficulties include:

- Clarity and Relevance: Ensuring that the report is clear and relevant to the audience is challenging. Project reports need to convey complex information in a simple and understandable way, catering to various stakeholders with different levels of expertise.

- Data Accuracy: Gathering accurate and up-to-date data can be difficult, especially in large and complex projects. Inaccurate data can lead to incorrect assessments of project performance.

- Balancing Detail: Striking the right balance between providing enough detail for informed decision-making and avoiding overwhelming the audience with excessive information can be tricky. Reports should offer enough detail to be useful but not so much that they become unwieldy.

- Consistency and Standardization: Maintaining consistency in reporting across projects and phases is difficult. For meaningful comparisons, project reports should follow a standard structure and key performance indicators; yet, modifying these standards to match the unique elements of each project can be difficult.

3. (20 points)

Consider the following network for conducting a 2-week (10 working days) computer training  class:

a. Find the critical path.

As per the network diagram, the critical path is: A-B-E

Total duration: 12 days.

Normal Cost: $500+$200+$300 = $1000.

Activities which can be crashed: A-B-E

b. Find the crash cost per day.

Crashing cost per day =Crash CostCrash Time

| Days | Crash Cost |
| --- | --- |
| A | $200 |
| B | $175 |
| C | $225 |
| D | $500 |
| E | $550 |

c. Which activities should be crashed to meet a project deadline of 10 days with a minimum  cost? Assume partial crashing.

To complete the project in 10 days, it must be crashed by 2 days.

B can be crashed for 1 day and A for 1 day.

d. Find the new cost.

Crashing Cost = $200+$175 = $375.

4. (20 points)

Consider the following activity information and the constraint that the project must be completed  in 16 weeks.

In addition, activities c, f, h, and i may be crashed as follows. Assume partial crashing.

Find the best schedule and its cost.

Network diagram:-

1

2

3

4

5

6

7

Start

End

A

C

B

E

D

F

G

I

H

Possible flows:

- A-D-H with duration 3+7+5 = 15 wks

- B-E-H with duration 6+5+5= 16 wks

- C-F-H with duration 8+10+5 = 23 wks

- C-G-I with duration 8+4+6 = 18 wks

Critical path:

- C-F-H with project duration 23 wks.

Considering the additional cost per week among the critical activities, activity H shall be crashed first.

Possible Flows:

- A-D-H with duration 3+7+2 = 12

- B-E-H with duration 6+5+2= 13

- C-F-H with duration 8+10+2 = 20

- C-G-I with duration 8+4+6 = 18

Critical path:

- C-F-H with project duration 20 wks

Considering the additional cost per week among the critical activities, activity F shall be crashed second.

Possible flows:

- A-D-H with duration 3+7+2 = 12 wks

- B-E-H with duration 6+5+2= 13 wks

- C-F-H with duration 8+6+2 = 16 wks

- C-G-I with duration 8+4+6 = 18 wks

The new critical path is C-G-I with project duration 18 wks.

Considering the additional cost per week among the critical activities, activity I shall be crashed third.

Possible flows:

- A-D-H with duration 3+7+2 = 12

- B-E-H with duration 6+5+2= 13

- C-F-H with duration 8+6+2 = 16

- C-G-I with duration 8+4+3 = 15

The Critical path is C-F-H with project duration 16.

To further decrease the project duration, we shall crash the fourth crashable activity.

Possible flows:

- A-D-H with duration 3+7+2 = 12 wks

- B-E-H with duration 6+5+2= 13 wks

- C-F-H with duration 7+6+2 = 15 wks

- C-G-I with duration 7+4+3 = 14 wks

The Critical path is C-F-H with project duration 15 wks.

Thus by making an investment of $100, we can crash the project duration from 23 weeks to 15 weeks.

5. (20 points)

a. A software development project at day 70 exhibits an actual cost of $78,000 and a scheduled  cost of $84,000. The software manager estimates a value completed of $81,000. What are the  cost and schedule variances and CSI? Estimate the time variance.

- Actual Cost (AC) = $78,000

- Scheduled Cost (PV) = $84,000

- Estimated Value (EV) = $81,000

AT (actual time) = 70 days.

Cost variance = EV – AC = $81,000 - $78,000 = $3,000

Schedule variance= EV – PV = $81,000 - $84,000 = -$3000

CPI = EV/AC = 1.03

SPI = EV/PV = 0.96

CSI = EV2/(AC)(PV)

= ($81,000)2/($78,000)($84,000)

= 6,561,000,000 / 6,552,000,000

= 1.001

TV = SV/Slope

Where slope = PV/Days ⇒ $84,000/70 = $1,200

SV = EV - PV ⇒ $81,000 - $84,000 = -$3,000

TV =  -$3,000/$1,200 = -2.5

b. A consulting project has an actual cost in month 10 of $23,000, a scheduled cost of $17,000, and a value completed of $20,000. Find the schedule and cost variances and the three indexes.

- Actual Cost (AC) = $23,000

- Actual Time (AT) = $10

- Planned Value (PV) = $17,000

- Earned Value (EV) = $20,000

Schedule Variance 	=  EV - PV

= 20000 - 17000

= 3000

Cost Variance 		= EV - AC

= 20000 - 23000

= - 3000

Indexes:

CPI	= EV / AC

= 20000 / 23000

= 0.869565217

= 0.87

SPI	= EV / PV

= 20000 / 17000

= 1.17647059

= 1.18

CSI 	= CPI - SPI

= 0.87 x 1.18

= 1.0266

= 1.027